## Sheet1
summary | Assignee | TimeTracking | status | Time Spent + Remaining Estimate | Issue type | Start Date | End Date
Start capstone project |  | 0% | In Progress | 0d | Epic | 2020-09-29 | 2020-10-25
In the process |  | 0% | To Do | 0d | Epic | 2020-10-26 | 2020-11-23
FCPM Sprint 1 | [5 empty] | 2020-09-29 | 2020-10-04
Comment | Đức Đỗ | 100% | Done | 2d | Task | 2020-10-02 | 2020-10-04
FCPM Sprint 2 | [5 empty] | 2020-09-29 | 2020-10-04
Search and filter forum | Đức Đỗ | 100% | Done | 4d | Task | 2020-10-05 | 2020-10-08
Create common upload file | (FUHL STUDENT) Bùi Trung Kiên | 100% | Done | 1m | Task | 2020-10-05 | 2020-10-08
Create common send email | (FUHL STUDENT) Bùi Trung Kiên | 100% | Done | 3m | Task | 2020-10-09 | 2020-10-11
Create notification component lecture | Nguyen Ngoc Khanh - K11 FUG HN | 100% | Done | 1w 2d | Task | 2020-10-05 | 2020-10-11
Create booking lecturers feature 22222222222 | Nguyen Ngoc Khanh - K11 FUG HN | 100% | Done | 1w 2d | Task | 2020-10-05 | 2020-10-11
Create capstone project detail page | (K12_HN) Nguyen Minh Khang | 100% | Done | 1w 2d | Task | 2020-10-05 | 2020-10-11
Register project to admin | Nguyen Ngoc Khanh - K11 FUG HN | 100% | Done | 2d | Task | 2020-09-29 | 2020-10-04
Create login with google account | (FUHL STUDENT) Bùi Trung Kiên | 100% | Done | 4d | Task | 2020-09-29 | 2020-10-04
View detail information of user | (K12_HN) Nguyen Minh Khang | 100% | Done | 1w 1d | Task | 2020-09-29 | 2020-10-04
Show list lecturers and booking | (K12_HN) Nguyen Duc Long | 100% | Done | 1w 1d | Task | 2020-09-29 | 2020-10-04
Post | Đức Đỗ | 100% | Done | 4d | Task | 2020-09-29 | 2020-10-01
FCPM Sprint 3 | [5 empty] | 2020-10-12 | 2020-10-17
Append send email to register project | (FUHL STUDENT) Bùi Trung Kiên | 100% | Done | 1w 2d | Task | 2020-10-12 | 2020-10-18
Append send email to booking lecturers | (K12_HN) Nguyen Minh Khang | 100% | Done | 1w 2d | Task | 2020-10-12 | 2020-10-18
Append upload file to forum | Nguyen Ngoc Khanh - K11 FUG HN | 100% | Done | 1w 1d | Task | 2020-10-12 | 2020-10-18
Append upload file to register project | (K12_HN) Nguyen Duc Long | 100% | Done | 1w 2d | Task | 2020-10-12 | 2020-10-18
Create confirm join team feature | Đức Đỗ | 100% | Done | 1w 2d | Task | 2020-10-12 | 2020-10-18
Create group for chatting | Đức Đỗ | 100% | Done | 1w 3d | Task | 2020-10-09 | 2020-10-11
FCPM Sprint 4 | [5 empty] | 2020-10-19 | 2020-10-25
Trainning department view infomation, status of list student | Đức Đỗ | 0% | In Progress | 0d | Task | 2020-10-19 | 2020-10-25
Trainning department request information to admin | Đức Đỗ | 0% | In Progress | 0d | Task | 2020-10-19 | 2020-10-25
Trainning department view and edit the list of registered projects | Đức Đỗ | 0% | In Progress | 0d | Task | 2020-10-19 | 2020-10-25
Admin view list capstone project | (FUHL STUDENT) Bùi Trung Kiên | 0% | In Progress | 0d | Task | 2020-10-19 | 2020-10-25
Admin accept or reject project | (FUHL STUDENT) Bùi Trung Kiên | 0% | In Progress | 0d | Task | 2020-10-19 | 2020-10-25
FCPM Sprint 5 | [5 empty] | 2020-10-26 | 2020-11-08
Daily report of member to leader |  | 0% | To Do | 0d | Task | 2020-10-26 | 2020-11-08
Weekly report of leader to lecturer |  | 0% | To Do | 0d | Task | 2020-10-26 | 2020-11-08
Detail project for admin |  | 0% | To Do | 0d | Task | 2020-10-26 | 2020-11-08
FCPM Sprint 6 | [5 empty] | 2020-11-09 | 2020-11-23
Auto upload report from jira |  | 0% | To Do | 0d | Task | 2020-11-09 | 2020-11-23
Dashboard all project for admin |  | 0% | To Do | 0d | Task | 2020-11-09 | 2020-11-23
Create dashboard statistical of projects |  | 0% | To Do | 0d | Task | 2020-11-09 | 2020-11-23
[màn hình login] lỗi login không báo khi không tồn tại người dùng trong DB | (FUHL STUDENT) Bùi Trung Kiên | 0% | Done | 0d | Bug | 2020-11-04 | 2020-11-04
[Forum] chưa fomat validate, k điên gì vẫn add post dc | (FUHL STUDENT) Bùi Trung Kiên | 0% | To Do | 0d | Bug | 2020-11-06 | 2020-11-06
[Forum] chưa fomat comment, k điên gì vẫn comment dc | (FUHL STUDENT) Bùi Trung Kiên | 0% | To Do | 0d | Bug | 2020-11-06 | 2020-11-06

## Sheet2
id | assignee | end_date | start_date | status | summary | time_spent | time_tracking | week | capstone_project_id
117 | Đức Đỗ | 2020-10-04 | 2020-10-02 | Done | Comment | 2d | 100 | 1 | 17
118 | Đức Đỗ | 2020-10-08 | 2020-10-05 | Done | Search and filter forum | 4d | 100 | 1 | 17
119 | (FUHL STUDENT) Bùi Trung Kiên | 2020-10-08 | 2020-10-05 | Done | Create common upload file | 1m | 100 | 1 | 17
120 | (FUHL STUDENT) Bùi Trung Kiên | 2020-10-11 | 2020-10-09 | Done | Create common send email | 3m | 100 | 1 | 17
121 | Nguyen Ngoc Khanh - K11 FUG HN | 2020-10-11 | 2020-10-05 | Done | Create notification component | 1w 2d | 100 | 1 | 17
122 | Nguyen Ngoc Khanh - K11 FUG HN | 2020-10-11 | 2020-10-05 | Done | Create booking lecturers feature | 1w 2d | 100 | 1 | 17
123 | (K12_HN) Nguyen Minh Khang | 2020-10-11 | 2020-10-05 | Done | Create capstone project detail page | 1w 2d | 100 | 1 | 17
124 | Nguyen Ngoc Khanh - K11 FUG HN | 2020-10-04 | 2020-09-29 | Done | Register project to admin | 2d | 100 | 1 | 17
125 | (FUHL STUDENT) Bùi Trung Kiên | 2020-10-04 | 2020-09-29 | Done | Create login with google account | 4d | 100 | 1 | 17
126 | (K12_HN) Nguyen Minh Khang | 2020-10-04 | 2020-09-29 | Done | View detail information of user | 1w 1d | 100 | 1 | 17
127 | (K12_HN) Nguyen Duc Long | 2020-10-04 | 2020-09-29 | Done | Show list lecturers and booking | 1w 1d | 100 | 1 | 17
128 | Đức Đỗ | 2020-10-01 | 2020-09-29 | Done | Post | 4d | 100 | 1 | 17
129 | (FUHL STUDENT) Bùi Trung Kiên | 2020-10-18 | 2020-10-12 | Done | Append send email to register project | 1w 2d | 100 | 1 | 17
130 | (K12_HN) Nguyen Minh Khang | 2020-10-18 | 2020-10-12 | Done | Append send email to booking lecturers | 1w 2d | 100 | 1 | 17
131 | Nguyen Ngoc Khanh - K11 FUG HN | 2020-10-18 | 2020-10-12 | Done | Append upload file to forum | 1w 1d | 100 | 1 | 17
132 | (K12_HN) Nguyen Duc Long | 2020-10-18 | 2020-10-12 | Done | Append upload file to register project | 1w 2d | 100 | 1 | 17
133 | Đức Đỗ | 2020-10-18 | 2020-10-12 | Done | Create confirm join team feature | 1w 2d | 100 | 1 | 17
134 | Đức Đỗ | 2020-10-11 | 2020-10-09 | Done | Create group for chatting | 1w 3d | 100 | 1 | 17
135 | Đức Đỗ | 2020-10-25 | 2020-10-19 | In Progress | Trainning department view infomation, status of list student | 0d | 0 | 1 | 17
136 | Đức Đỗ | 2020-10-25 | 2020-10-19 | In Progress | Trainning department request information to admin | 0d | 0 | 1 | 17
137 | Đức Đỗ | 2020-10-25 | 2020-10-19 | In Progress | Trainning department view and edit the list of registered projects | 0d | 0 | 1 | 17
138 | (FUHL STUDENT) Bùi Trung Kiên | 2020-10-25 | 2020-10-19 | In Progress | Admin view list capstone project | 0d | 0 | 1 | 17 | 62 | 17 | 21
139 | (FUHL STUDENT) Bùi Trung Kiên | 2020-10-25 | 2020-10-19 | In Progress | Admin accept or reject project | 0d | 0 | 1 | 17
140 | \N | 2020-11-08 | 2020-10-26 | To Do | Daily report of member to leader | 0d | 0 | 1 | 17
141 | \N | 2020-11-08 | 2020-10-26 | To Do | Weekly report of leader to lecturer | 0d | 0 | 1 | 17
142 | \N | 2020-11-08 | 2020-10-26 | To Do | Detail project for admin | 0d | 0 | 1 | 17
143 | \N | 2020-11-23 | 2020-11-09 | To Do | Auto upload report from jira | 0d | 0 | 1 | 17
144 | \N | 2020-11-23 | 2020-11-09 | To Do | Dashboard all project for admin | 0d | 0 | 1 | 17
145 | \N | 2020-11-23 | 2020-11-09 | To Do | Create dashboard statistical of projects | 0d | 0 | 1 | 17